## BACKLOG
| Priotity [0-High 1-Medium 2-Low] | Activity Details | Who takes?
2 | 0 | ETL - Filter the table version | Gustavo
| 0 | CSV - Insert Files | Viet
0 | 0 | Descriptive - Graphs | Janet
1 | 0 | Forecast - Predict CAI - Script | CAI
| 0 | Forecast - Predict - Interface
0 | 0 | Interface - Left Menu | Cylia
1 | 1 | Descriptive - Update the Graphs with Filters | Indu
0 | 1 | Descriptive - Heatmap MAPS
0 | 1 | Forecast - Program
1 | 2 | ETL - Update Address Table from Google MAPS;
2 | 2 | CSV-ETL - Link modules
0 | 2 | Forecast - Enterprise
| 2 | ETL - Merged table directly (without changes)
| 3 | Documentation (Motivation, Solutions, etc)
| 3 | Presentation

## Sprints
Sprint | 21 May
- Discuss Backlog (Activities and Priorit)
- Divide the Tasks
- CAI - want install Django?